## Report
Date | Task Name | Status | Person
2025-04-04 | Brainstorm project ideas | Complete | Everyone
2025-04-05 | Create github repo | Complete | Adam Rodi
2025-04-06 | Decide on project idea | Complete | Everyone
2025-04-06 | Design module outlines | Complete | Everyone
2025-04-06 | Define input data format | Complete | Everyone
2025-04-06 | Design module communication diagram | Complete | Everyone
2025-04-06 | Complete PA1 powerpoint report | Complete | Everyone
2025-04-14 | Added Avg Volume Functions | In Progress | Caleb Viverito
2025-04-15 | Added exporting Avg Volume Functions to pickle file | In Progress | Caleb Viverito
2025-04-18 | Add exception handling to functions | Complete | Adam Rodi
2025-04-27 | Implement price visualization functions | Complete | Adam Rodi